## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 22.1.18 | Proposals for acquisition of land for housing development, establishment of crofts, development of existing buildings for community use | ACC, RHJ | 2019 | Pending | Awaiting outcome of meeting of ACC, Trust, Highland Council and SLC
2 | 22.1.18 | Replacement of chairs for Clachan Church | FM | April/May 2019 | Pending | Services and chairs to be moved from Cammusterach to Clachan
3 | 22.1.18 | Redevelopment and creation of paths | JG | 2019 | Pending
4 | 22.1.18 | Polytunnel/allotment project | LT, KM | 12.6.19 | Pending | Lease to be signed between Trust and ACC
5 | 3.5.18 | Plan for recreational space | Sports group | 1905-07-11 | Pending | Development of proposals.
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending
7 | 19.9.18 | Arrangements for Community Fund | OK, JG, LT, TM, AF | 1905-07-11 | Pending | Forum to invite views of community on proposals of working group
8 | 13.3.19 | Community Woodland project | MM | 1.10.19 | Pending | Fundiing for feasibility study to be obtained
9 | 12.6.19 | Bealach Viewpoint | JG | 30.6.19 | Pending | JG to make available plan of proposed viewpoints
10 | 12.6.19 | Helipad | CW | 2019 | Pending | Survey to be carried out and costings obtained