## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 22.1.18 | Proposals for acquisition of land for housing development, establishment of crofts, development of existing buildings for community use | ACC, RHJ | 2020 | Pending | Funding for feasibility studies on proposed sites
2 | 22.1.18 | Replacement of chairs for Clachan Church | FM | April/May 2019 | Pending | Decision by General Trustees awaited/use of chairs already in Clachan
3 | 22.1.18 | Redevelopment and creation of paths | JG | 2020 | Pending
4 | 22.1.18 | Polytunnel/allotment project | LT, KM |  | Pending | Funding for development of site
5 | 3.5.18 | Plan for recreational space | Sports group |  | Pending | Fundiing for feasibility study to be obtained
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending | ?????
7 | 19.9.18 | Arrangements for Community Fund | OK, JG, LT, TM, AF |  | Pending | Presentations delivered on different option
8 | 13.3.19 | Community Woodland project | MM | 1.10.19 | Pending | Fundiing for feasibility study to be obtained
9 | 12.6.19 | Bealach Viewpoint | JG | 30.6.19 | Pending | JG to make available plan of proposed viewpoints
10 | 12.6.19 | Helipad | CW | 2019 | Pending | Planning permission to be applied for
11 | 2.10.19 | Tourism Management Group | JW/JG | 2019-11-01 | Pending | Group formation at initial meeting
12 | 2.10.19 | Research project on traffic over Bealach | JG/MS | 2020 | Pending | Identification of researchers
13 | 2.10.19 | Governance of Forum | MH | 2020 | Pending | Review Group to be formed to look at issues
14 | 2.10.19 | Complaint about degradation of road during extraction of timber and question of compensation | AM | 2019-11-01 | Pending | AM to raise with Scottish Woodland
15 | 2.10.19 | E Bikes | RC | 2019-11-01 | Pending | Bikes to be delivered and open session for use and maintenance
16 | 2.10.19 | EV Charger | RC |  | Pending | Application to Local Energy Scotland to be submitted