## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 22.1.18 | Proposals for acquisition of land for housing development, establishment of crofts, development of existing buildings for community use | ACC, RHJ | 2020 | Pending | Funding for feasibility study obtained and public meeting to be held
2 | 22.1.18 | Replacement of chairs for Clachan Church | FM | 1905-07-12 | Pending | Decision by General Trustees awaited/use of chairs already in Clachan
3 | 22.1.18 | Redevelopment and creation of paths | JG | 2020 | Pending
4 | 22.1.18 | Polytunnel/allotment project | LT, KM |  | completed
5 | 3.5.18 | Plan for recreational space | Sports group |  | Pending | Sarah's gym operating. Awaiting proposals for development of Steading/Hartfield before further steps
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending | ?????
7 | 19.9.18 | Arrangements for Community Fund | OK, JG, LT, TM, AF |  | Pending | Detailed proposal for SCIO to be prepared
8 | 13.3.19 | Community Woodland project | MM | 1905-07-13 | Pending | Meeting to take place on Monday 20 January 2020
9 | 12.6.19 | Bealach Viewpoint | JG | 30.6.19 | Pending | JG to make available plan of proposed viewpoints
10 | 12.6.19 | Helipad | CW |  | Pending | planning permission granted. Completion spring 2021
11 | 2.10.19 | Tourism Management Group | JW/JG | 2019-11-01 | Pending | Survey of local businesses to be undertaken
12 | 2.10.19 | Research project on traffic over Bealach | JG/MS | 2020 | Pending | Identification of researchers
13 | 2.10.19 | Governance of Forum | MH | 2020 | Pending | Further discussions to be held
14 | 2.10.19 | Complaint about degradation of road during extraction of timber and question of compensation | AM |  | Completed | Donations to be made to Sheildaig Community Council by Kishorn Port and Scottish Woodland
15 | 2.10.19 | E Bikes | RC |  | completed
16 | 2.10.19 | EV Charger | RC |  | Pending | Feasibility study to be carried out by Applejuice