## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 18.11.20 | Acquisition from Trust of Land at Hydro field and Torgarve | ACC, RHJ | 2021-03-01 | Pending | conveyancing ongoing
2 | 18.11.20 | Replacement of chairs for Clachan Church | FM |  | Pending | Decision by General Trustees awaited/use of chairs already in Clachan
3 | 22.1.18 | Redevelopment and creation of paths | JG |  | Pending
4 | 18.11.20 | Camusterrach Housing Project | ACC |  |  | Construction to start Mid Dec/Jan. Name competition to be launched
5 | 18.11.20 | Pubic Toilets | ACC |  | Pending | Funding being sought for regular maintenance and upgrade
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending | ?????
7 | 18.11.20 | Arrangements for Community Fund | FM, DM, JG, TM |  | Pending | Draft SCIO to be prepared
8 | 18.11.20 | Acquisition of Camusterrach Church | ACC |  | Pending | Interest noted. Funding required.
9 | 18.11.20 | Bealach Viewpoints and signage | KM |  | Pending | Enquiries to be made of Roads Officer
10 | 12.6.19 | Helipad | CW | Spring 2021 | Pending | planning permission granted. Completion spring 2021
11 | 18.11.20 | Tourism Management Group | JW/JG |  | Pending | Draft Strategy to be prepared
12
13 | 18.11.20 | Trust properties available for community use | ACC/RHJ |  | Pending | Discussion to be held to identify buildings available and conditions
14 | 18.11.20 | Complaint of damage & inconvenience from construction traffic to new hydro scheme | KM |  |  | Approach to Roads Officer
15 | 18.11.20 | Covid Response | ACC |  |  | Ongoing support. 4 Chromebooks available
16 | 18.11.20 | EV Charger | RC |  | Pending | Detailed design for project to be completed Dec 2020. Installation 2021 subject to funding and access to site at Stack Yard