## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 18.11.20 | Acquisition from Trust of Land at Hydro field and Torgarve | ACC, RHJ | 2021-03-01 | Pending | conveyancing ongoing
2 | 18.11.20 | Camusterrach Housing Project | ACC |  |  | Construction to start Mid Dec/Jan. Name competition to be launched
3 | 18.11.20 | Pubic Toilets | ACC |  | Pending | Upgrading
4 | 18.11.20 | Acquisition of Camusterrach Church | ACC |  | Pending | discussions ongoing. Valuation obtained and business plan being prepared
5 | 18.11.20 | Covid Response | ACC |  |  | Ongoing support. 4 Chromebooks available
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending | ?????
7 | 18.11.20 | Arrangements for Community Fund | FM, DM, JG, TM |  | Pending | Further draft of SCIO to be undertaken; clarification of payment from CRF Hydropower to be obtained
8 | 18.11.20 | EV Charger | RC |  | Pending | Funding application to Ofgem Energy Redress Scheme
9 | 18.11.20 | Tourism Management Group | JW/JG |  | Pending | Draft Strategy prepared. Action plans to be devised.
10 | 12.6.19 | Helipad | CW | Spring 2021 | Pending | Construction underway
11 | 18.11.20 | Trust properties available for community use | ACC/RHJ |  | Pending | Appliecation to be made direct to Trust.
12 | 10.2.21 | Round house repairs | LK |  |  | Reeds to be obtained from Keppoch barn
13 | 18.11.20 | Attendance of Forum representatives at Trust meetings | RHJ |  |  | TBC
14 | 10.2.21 | Internet connection | JB |  |  | Information awaited from BT Openreach