## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 18.11.20 | Acquisition from Trust of Land at Hydro field and Torgarve | ACC, RHJ | 2021-03-01 | Completed
2 | 18.11.20 | Camusterrach Housing Project | ACC |  | Pending | Construction ongoing with completion expected Nov 2021. Named An Toll Ban
3 | 18.11.20 | Pubic Toilets | ACC |  | Pending | Touch free facilities installed. Paid entry system expected May 2021
4 | 18.11.20 | Acquisition of Camusterrach Church | ACC |  | Pending | Following approval at AGM funding to be sought for feasibility study.
5 | 18.11.20 | Covid Response | ACC |  |  | Support continuing including food boxes and meals on wheels
6 | 3.5.18 | Conservation policy of Trust | AM |  | Pending | ?????
7 | 18.11.20 | Arrangements for Community Fund | FM, DM, JG, TM |  | Pending | Legal formalities being completed
8 | 18.11.20 | EV Charger | RC |  | Pending | Funding application outstanding
9 | 18.11.20 | Tourism Management Group | JW/JG |  | Pending | Strategy prepared and circulated. Management plans drafted. Focus on "wild" camping, overnight parking of mobile homes and waste management. Highland Council appointing Rangers.
10 | 12.6.19 | Helipad | CW | Spring 2021 | Pending | Construction largely completed. Grass to be sown and lights and windsock to be considered by designer
11 | 18.11.20 | Trust properties available for community use | ACC/RHJ |  | Pending | Trust to engage with ACC re applications
12 | 10.2.21 | Round house repairs | LK |  |  | Plans for refurbishment following insurance claim. Possible learning opportunity.
13 | 18.11.20 | Attendance of Forum representatives at Trust meetings | RHJ |  |  | TBC
14 | 10.2.21 | Internet connection | JB |  |  | Meeting to include ACC, Openreach and MP to discuss costs