## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 01.09.21 | Trust properties available for rental |  |  | Pending | Identification of tenants for Torgarve Cottage and 8 Milton. Update on rental of the Smiddy.
2 | 18.11.20 | Camusterrach Housing Project | ACC |  | Pending | Construction ongoing with completion expected Nov 2021. Named An Toll Ban
3 | 18.11.20 | Acquisition of Camusterrach Church | ACC |  | Pending | Following approval at AGM funding to be sought for feasibility study.
4 | 18.11.20 | Arrangements for Community Fund | FM, DM, JG, TM |  | Pending | Legal formalities being completed
5 | 18.11.20 | EV Charger | ACC |  | Pending | Feasibility Study to use Applejuice due in December
6 | 18.11.20 | Tourism Management Group | JW/JG |  | Pending | Webinar and questionaire to be circulated to residents to obtain views for future strategy. Funding application to Coastal Communities to be determined end September.
7 | 12.6.19 | Helipad | CW |  | Pending | Windsock and landing lights outstanding
8 | 18.11.20 | Trust properties available for community use | ACC/RHJ |  | Pending | Trust to engage with ACC re applications
9 | 10.2.21 | Round house repairs | OK/AM |  |  | Discussions between Archeological Society and Trust about future use and maintenance
10 | 10.2.21 | Internet connection | JB |  |  | Meeting to include ACC, Openreach and MP to discuss costs
11
12
13
14