## Sheet1
Number | Meeting date | Action | Lead person | Target date | Status | Comment
1 | 01.09.21 | Trust properties available for rental |  |  | Pending | Update on completion of works at the Old Forge.
2 | 18.11.20 | Camusterrach Housing Project | ACC |  | Pending | identification of successful applicants and entry dates
3 | 18.11.20 | Acquisition of Camusterrach Church | ACC |  | Pending | Consultation with community on proposed use on 20 January 2022
4 | 18.11.20 | Arrangements for Community Fund | FM, DM, JG, TM |  | Pending | Legal formalities being completed
5 | 18.11.20 | EV Charger | ACC |  | Pending | Feasibility Study to use Applejuice due in December
6 | 18.11.20 | Tourism Management Group | JW/JG |  | Pending | development of Group as Tourism Association. Consultatiion on Strategy. Brighter face project. Issue of public safety
7 | 12.6.19 | Helipad | CW |  | Pending | Windsock and landing lights outstanding
8 | 18.11.20 | Trust properties available for community use | ACC/RHJ |  | Pending | Trust available for discussion about proposed use of buildings including the Steading, the old stables and the cart shed.
9 | 10.2.21 | Round house repairs | OK/AM |  | Pending | Insurance claim being progressed. Awaiting quotations for repairs. Trust inviting expressions of interest from group willing to take on responsibilities for maintenance and use.
10 | 10.2.21 | Internet connection | JB |  | Pending | What action to be taken and by whom with regard to costs of access to fibre optic
11 | 8.12.21 | Funding of Community Hall | JM |  | pending | Discussions between JM and RHJ with regard to financial assistance
12 | 8.12.21 | List of proposed signage | JG |  | Pending | Availability for viewing
13 | 8.12.21 | Proposed residents' parking and yellow lines on Shore Street | JG |  | Pending | Details of proposals
14 | 8.12.21 | Adoption of member of the community as Trustee of Applecross Trust | RHJ |  | Pending | RHJ to report on discussions amongst Trustees
15 | 8.12.21 | Proposals for use of the sums received from the sale of the hydro field and Torgarve | RHJ |  | Pending | RHJ to report on discussions amongst Trustees
16 | 8.12.21 | discussions around development of new 5 year plan | RHJ |  | Pending | Proposals how discussions with community to take place
17 | 8.12.21 | Review of Forum | JW/TO'H |  | Pending | Progress